Example Timeline/Workplan for the MAPP Process

The example timeline / workplan below uses an 18-month timeframe.  The activities included under each phase are examples of activities that could be conducted.  As emphasized throughout the MAPP guidance, communities should implement each phase in the way that best meets their community characteristics and needs.  The timeline focuses on the planning aspect of MAPP; the implementation and evaluation activities (the Action Cycle) should be sustained long after the MAPP timeline below ends.

The darker shading shows the timeline for each entire phase; the lighter shading underneath shows the timeline for various activities within each phase.

| MAPP Phase / Description of Activity | Month (using a 1 ½ year timeline) |
| --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| Organize for Success / Partnership Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Determine why the MAPP process is needed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify, organize, and recruit participants |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design the planning process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Assess resource needs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct a readiness assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop a workplan, timeline, and other tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Visioning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare for and design the visioning process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hold visioning sessions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Celebrate successes and achievements to date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 MAPP Assessments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Community Themes and Strengths Assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify subcommittee, approaches, and resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hold community dialogues and focus groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop/disseminate/collect a community survey |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct interviews with residents / key leaders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Compile results/identify challenges and opportunities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Local Public Health System Assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare for the LPHSA/ establish subcommittee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discuss the Essential Services/identify org. activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Respond to the performance measures instrument |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discuss results/identify challenges and opportunities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| MAPP Phase / Description of Activity | Month |
| --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| Community Health Status Assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct data collection of core indicators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Select and collect additional indicators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyze the data / create a health profile |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Disseminate health profile |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish a system to monitor data over time |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify CHSA challenges and opportunities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Forces of Change Assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare for the Forces of Change Assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hold brainstorming session with committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Simplify list / identify threats and opportunities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify Strategic Issues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Celebrate successes and completion of assessments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify potential strategic issues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discuss issues-why they are strategic and urgency |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Consolidate strategic issues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Arrange issues in priority order |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Formulate Goals and Strategies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop goal statements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop strategy alternatives and barriers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Explore implementation details |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Select and adopt strategies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft the planning report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Celebrate successes and recognize achievements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Action Cycle* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organize for action |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop objectives and agree on accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop action plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Coordinate action plans and implement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare for evaluation / determine the methodology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Gather evidence and justify conclusions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Share results |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

*  The Action Cycle should continue after the timeline ends; activities should be incorporated into organizational activities and be sustained throughout the community.